Work Package 1: Field sampling and chemical analysis

1.1) Instrument soil plots in sub-catchments and their perennial streams for capture of water flowing through the watershed.

Start of activity: 10 2011

Completion of activity: 09 2012

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Procurement of soil water sampling equipment | Lysimeter, bottles, tubing, pump | 10.11 – 03.12 |  | Equipment |
| 1.1.2 | Field survey, identify sampling sites | Study of maps, travel to site | 04.12 – 06.12 |  | Maps, Travel |
| 1.1.3 | Install sampling equipment in sub-catchments | Field work | 04.12 – 09.12 |  | Travel |
| 1.1.4 |  |  |  |  |  |
| 1.1.5 |  |  |  |  |  |

1.2) Conduct seasonal synoptic study of water and soil chemical and physical characteristics in the whole watershed, including pools of nutrients in the soils.

Start of activity: 01 2012

Completion of activity: 12 2013

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.2.1 | Collect and synthesize background data | Land use, history, agricultural practice, sewage, climate | 01.12 – 09.12 |  |  |
| 1.2.2 | Field survey |  | 04.12 – 07.13 |  |  |
| 1.2.2.1 | Identify sampling sites | Different: land use, crops, soil type, topography | 04.12 – 06.12 |  | Maps |
| 1.2.2.2 | Synoptic sampling of soil | Field work | 07.12 – 07.12 |  | Travel |
| 1.2.2.3 | Seasonal surveys of surface water | Field work in Summer – fall – winter - spring | 07.12 – 06.13 |  | Travel |
| 1.2.2.4 | Analysis of nutrient fractionations in water from soil plots and synoptic study of surface waters | Tot-P and PO4 in unfiltered and filtered water samples. Emphasis on Particulate bound P | 08.12 – 07.13 |  | Chemistry lab |
| 1.2.2.5 | Analysis of pools of P and physicochemical characteristics of soil from plots and synoptic study | Tot-P and PO4 in unfiltered and filtered water samples. Emphasis on Particulate bound P | 08.12 – 12.12 |  | Chemistry lab |
| 1.2.2.6 | Analysis of major anions and cations in water | H, Ca, Mg, Na, K, SO4, NO3, Cl, HCO3, TOC | 08.12 – 07.13 |  | Chemistry lab |
| 1.2.3 | Monitoring of soil water in soil plots |  | 01.13 – 12.13 |  | 1.1 |
| 1.2.3.1 | Analysis of nutrient fractionations in soil pools | Tot-P and PO4 in unfiltered and filtered water samples. Emphasis on Particulate bound P | 01.13 – 12.13 |  | Chemistry lab |
| 1.2.3.3 | Analysis of major anions and cations in water | H, Ca, Mg, Na, K, SO4, NO3, Cl, HCO3, TOC | 01.13 – 12.13 |  | Chemistry lab |

1.3) Episode studies of water chemistry of runoff from selected sub-catchments.

Start of activity: 04 2012

Completion of activity: MM YYY

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.3.1 | Field survey, identify sampling sites |  | 04.12 – 06.12 |  | Map, travel |
| 1.3.2 | Episode studies | Intense sampling during Periods of heavy rain after preceding dry conditions | 07.12 – 06.13 |  |  |
| 1.3.2.1 | Sampling campaigns | Capture 3 – 4 episodes | 07.12 – 06.13 |  | Auto-sampler (?), Travel |
| 1.3.4 | Nutrient fractionation | Tot-P and PO4 in unfiltered and filtered water samples. Emphasis on Particulate bound P | 07.12 – 06.13 |  | Chemistry lab |
| 1.3.5 | Chemical analysis of major anions and cations | H, Ca, Mg, Na, K, SO4, NO3, Cl, HCO3, TOC | 07.12 – 06.13 |  | Chemistry lab |

1.4) Nutrient fractions in river and surface water. By means of different sample pre-treatment determine important P fractions, with emphasis on particle bound P.

Start of activity: 01 2012

Completion of activity: MM YYYY

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.4.1 | Inter-calibration of chemical laboratories | Emphasis on tot-P and PO4 determination | 01.12 – 03.12 |  | Chemistry lab |
| 1.4.2 | P fractionation | Tot-P and PO4 in unfiltered and filtered water samples. Emphasis on Particulate bound P | 07.12 – 06.13 |  |  |
| 1.4.2.1 | P fractionation on water from soil plots |  | 01.13 – 12.13 |  | 1.2.3 |
| 1.4.4 | P fractionation on water from synoptic study |  | 01.13 – 12.13 |  | 1.2.2 |
| 1.4.5 | P fractionation on water from episode study |  | 07.12 – 06.13 |  | 1.3 |

1.5) Use the DGT sampler for passive collection of bio available P fraction as well as low molecular organic phosphorus compounds. The potential of new sediment dept profile probes will be examined (DGT, DET and peeper systems).

Start of activity: 07 2012

Completion of activity: 06 2013

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.5.1 | DGT sampling |  | 07.12 – 06.13 |  |  |
| 1.5.2 |  |  |  |  |  |
| 1.5.3 |  |  |  |  |  |
| 1.5.4 |  |  |  |  |  |
| 1.5.5 |  |  |  |  |  |

1.6) Monitoring other water quality indices (Chl-a, turbidity, pH, temperature, odour etc.) by means of a multiparameter water quality monitor (YSI 6600-2) in the Yuqiao reservoir, which helps to calibrate the model of algae bloom.

Start of activity: 07 2012

Completion of activity: 06 2013

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.6.1 | Water quality monitoring |  | 07.12 – 06.13 |  |  |
| 1.6.2 |  |  |  |  |  |
| 1.6.3 |  |  |  |  |  |
| 1.6.4 |  |  |  |  |  |
| 1.6.5 |  |  |  |  |  |

Work Package 2: Catchment processes - the influence of land-use and hydrology on nutrient fluxes into aquatic systems.

2.1) Study of soil-soil/water interactions in agricultural land used for different types of crops (1.1), draining into Yuqiao reservoir. Biogeochemical processes governing the nutrient flux from the soil to soil water will be studied on plot scales. Data on deposition and soil water chemistry from genetic horizons incl. ground water along topographic gradients in the sub-catchments (WP1.1) will be assessed. The relationship between soil pools and P fractions in solution will be studied in terms of hydro-biogeochemical processes governing the mobilization of P in relation to soil characteristics and overall soil water chemistry (WP1.2-6) using multivariate statistics (SIMCA-P).

Start of activity: 10 2011

Completion of activity: 10 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 2.1.1 | Inception and detailed project planning |  | 10.11 – 03.12 | Vogt/et al |  |
| 2.1.2 | Announcement and selection of PhD fellowship |  | 08.11 – 10.11 | Vogt |  |
| 2.1.3 | Study of soil-soil water interactions governing the mobilization of P |  | 01.13 – 12.13 | PhD/Vogt | 1.2-6 |
| 2.1.3.1 | Study relationship between chemical parameters in soil and soil water from soil plots using SIMCA-P |  | 01.13 – 12.13 | PhD/Vogt | 1.2 & 1.4, SIMCA-P |
| 2.1.3.2 | Hydro-biogeochemical process studies of soil and soil water chemistry along topographic gradients |  | 01.13 – 12.13 | PhD/Vogt | 1.2 & 1.4 |
| 2.1.3.3 | Relationship between soil P pools in soil and P fractions in water in soil plot and transect studies |  | 01.13 – 12.13 | PhD/Vogt | 1.1 |
| 2.1.4 | Dissemination | ≥ 1 statistical approch paper | 07.12 – 10.14 | ALL | 2.1 |
| 2.1.5 | PhD Dissertation |  | 10.14 – 10.14 | PhD/Vogt | 1 - 5 |

2.2) Mobilization and fluxes of bio-relevant nutrient fractions (WP1.4) will be studied through a regional survey (WP1.2) to identify hotspots and preferential hydrological flow-paths

Start of activity: 07 2012

Completion of activity: 06 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 2.2.1 | Flux calculations of bio-relevant nutrient fractions based on background data |  | 10.12 – 12.13 | PhD/Vogt | 1.1 |
| 2.2.2 | Flux calculations of bio-relevant nutrient fractions based on surface water (streams and lake) from synoptic study and hydrological data |  | 07.12 - 06.13 | PhD/Vogt | 1.2 & 1.4, runoff data |
| 2.2.3 | Identify important sources of P and N fractions to the reservoir |  | 01.14 – 06.14 | PhD/Vogt |  |
| 2.2.4 | Identify preferential hydrological flow-paths based on sources and fluxes as well as episode study using EMMA |  | 01.14 – 06.14 | PhD/Vogt | 2.4 |
|  | Dissemination | ≥ 1 pathway paper | 07.12 – 06.14 | ALL | 2.2 |

2.3) Process oriented studies of monitoring data from WP1.1 will be used to identify conceptual based and empirically founded  relationships between environmental pressures and changes to the levels of bio-available nutrient species in the lake. Speciation will be conducted with MINEQL+.

Start of activity: 04 2013

Completion of activity: 03 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 2.3.1 | Biogeochemical process assessment |  | 04.12 – 03.14 | PhD/Vogt |  |
| 2.3.1.1 | Speciation of soil water and stream water chemistry with MINEQL+ |  | 07.13 – 07.13 | PhD/Vogt | 1.2 & 1.3, MINEQL+ |
| 2.3.1.2 | Assessment of processes governing water chemistry in river and surface water based on studies in 2.1 |  | 04.12 – 03.14 | PhD/Vogt | 2.1 |
| 2.3.1.3 | Assessment of processes governing mobilization of P fractions to river and surface water based on studies in 2.1 |  | 04.12 – 03.14 | PhD/Vogt | 1.3 & 1.4, 2.1 |
| 2.3.1.4 | Inverse modelling of processes governing water chemistry based on deposition chemistry and soil water chemistry from plot studies using PHREEQ-C |  | 12.13 – 03.14 | PhD/Vogt | 1.2 |
| 2.3.2 | Effects of changes in pressures on bio-available nutrients | Climate change, land use change | 04.12 – 03.14 | PhD/Vogt |  |
| 2.3.3 | Dissemination | ≥ 1 process paper | 07.12 – 03.14 | ALL | 2.3 |

2.4) Episode studies of discharge and hydrochemistry data from 1iii will be studied to validate model hypotheses (WP3) of transport processes (WP2i-iii) and link between hydrological and chemical outwash processes.

Start of activity: 04 2012

Completion of activity: 12 2013

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 2.4.1 | Biogeochemical process assessment |  | 04.12 – 03.14 | PhD/Vogt |  |
| 2.4.2 | Assess hydrological response of nutrient fractions |  | 07.13 – 12.13 | PhD/Vogt | 1.3 & 1.4 |
| 2.4.3 | Assess hydrological flow-paths by EMMA study of episode data |  | 07.13 – 12.13 | PhD/Vogt | 1.3 |
| 2.4.4 | Dissemination | ≥ 1 episode paper | 07.12 – 12.13 | ALL | 2.4 |
| 2.4.5 |  |  |  |  |  |

2.5) Comparative study between Western Vansjø in Norway and Yuqiao reservoir.

Start of activity: 01 2012

Completion of activity: 06 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 2.5.1 | Collect and synthesize background data | Data from Yuqiao and vansjø | 01.12 – 09.12 | PhD/Vogt |  |
| 2.5.2 | Comparative study |  | 10.13 – 06.14 | PhD/Vogt | Data from Eutropia project |
| 2.5.3 | Dissemination | ≥ 1 comparative paper | 10.13 – 06.14 | ALL | 2.5 |
| 2.5.4 |  |  |  |  |  |
| 2.5.5 |  |  |  |  |  |

Work Package 3: Modelling of processes

3.1) The Soil and Water Assessment Tool (SWAT) is a river basin scale model that will beadapted and parameterized for the investigated sub-catchment of Yuqiao reservoir. The optimized model will be used test hypotheses of nutrient mobilization and hydrological runoff formation in sloped areas and how it matches observed episodic hydrological and chemical data from field studies (WP2).

Start of activity: 01 2012

Completion of activity: 06 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 3.1.1 | Collect and synthesize background data |  | 01.12 – 09.12 |  |  |
| 3.1.2 | Parameterize and run chemical models |  | 07.13 – 06.14 |  |  |
| 3.1.3 |  |  |  |  |  |
| 3.1.4 |  |  |  |  |  |
| 3.1.5 |  |  |  |  |  |

3.2) Changes in fluxes of nutrient fractions due to climate change and land management practices will be investigated by using downscaled climatologically scenarios.

Start of activity: 01 2014

Completion of activity: 09 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 3.2.1 | Assess responce to changes in pressures |  | 01.14 – 09.14 |  |  |
| 3.2.2 |  |  |  |  |  |
| 3.2.3 |  |  |  |  |  |
| 3.2.4 |  |  |  |  |  |
| 3.2.5 |  |  |  |  |  |

3.3) A system for cyanobacterial bloom pre-warning will be developed based on an existing 1-dimensional lake thermodynamics mode21 calibrated against high-frequency field observations and satellite imagery. The model will help alert scientists and managers to possible threats to Yuqiao Reservoir and assist in mitigation efforts.

Start of activity: 01 2014

Completion of activity: 09 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 3.3.1 | Develop system for pre-warning |  | 01.14 – 09.14 |  |  |
| 3.3.2 |  |  |  |  |  |
| 3.3.3 |  |  |  |  |  |
| 3.3.4 |  |  |  |  |  |
| 3.3.5 |  |  |  |  |  |

Work Package 4: Societal processes and management procedures

4.1) Map demographic and industrial patterns and urbanisation; land use pattern and agricultural production methods – also feeding into WP2.

Start of activity: 01 2012

Completion of activity: 09 2012

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 4.1.1 | Map land-use and demography |  | 01.12 – 09.12 |  |  |
| 4.1.2 |  |  |  |  |  |
| 4.1.3 |  |  |  |  |  |
| 4.1.4 |  |  |  |  |  |
| 4.1.5 |  |  |  |  |  |

4.2) Contextualise overall driving forces/processes and development patterns into regional conditions (Beijing-Tianjin), and local conditions (Yuqiao reservoir and Ji county)

Start of activity: 04 2012

Completion of activity: 12 2012

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 4.2.1 | Link societal drivers to conditions |  | 04.12 – 12.12 |  |  |
| 4.2.2 |  |  |  |  |  |
| 4.2.3 |  |  |  |  |  |
| 4.2.4 |  |  |  |  |  |
| 4.2.5 |  |  |  |  |  |

4.3) Identify actor categories and field structures, with the main focus on water and agricultural related fields, including production, policy-making, and management

Start of activity: MM YYYY

Completion of activity: MM YYYY

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 4.3.1 |  |  |  |  |  |
| 4.3.2 |  |  |  |  |  |
| 4.3.3 |  |  |  |  |  |
| 4.3.4 |  |  |  |  |  |
| 4.3.5 |  |  |  |  |  |

4.4) Conduct a survey covering different actor groups (e.g. farmers and local governmentofficials, and different farmer categories) with closed questions and common section and a tailor-made section. Conduct at least 100 semi-structured face-to-face interviews and 5 focus group interviews with representatives of central actor categories – in the case study area and at higher administrative levels of Tianjin and Beijing.

Start of activity:  07 2012

Completion of activity: 06 2013

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 4.4.1 | Questionnaire |  | 07.12 – 06.13 |  |  |
| 4.4.2 |  |  |  |  |  |
| 4.4.3 |  |  |  |  |  |
| 4.4.4 |  |  |  |  |  |
| 4.4.5 |  |  |  |  |  |

4.5) Analyse the role of knowledge and learning processes and how this creates particular practices: To what degree can information and learning help improve water quality compared with policy measures of pure incentives? Are path dependent processes causing lock-ins and next obstacles against achieving good water quality?

Start of activity: 01 2013

Completion of activity: 03 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 4.5.1 | Role of knowledge and learning |  | 01.13 – 03.14 |  |  |
| 4.5.2 |  |  |  |  |  |
| 4.5.3 |  |  |  |  |  |
| 4.5.4 |  |  |  |  |  |
| 4.5.5 |  |  |  |  |  |

4.6) Analyse management procedures at different administrative levels and how they are interacting in relation to issues like eutrophication. Identify bottlenecks and contradictions that might function as obstacles for an efficient water resource policy, and consider how they can be solved; paying particular attention to the issue of scale.

Start of activity: 10 2013

Completion of activity: 09 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 4.6.1 | Suggest management proceedures |  | 10.13 – 06.14 |  |  |
| 4.6.2 | Assess legitimimacy of policies |  | 04.14 – 09.14 |  |  |
| 4.6.3 |  |  |  |  |  |
| 4.6.4 |  |  |  |  |  |
| 4.6.5 |  |  |  |  |  |

Work Package 5: Nutrient management plan for Yuqiao reservoir

5.1) Apply the Circular Economy approach with nutrient at its cores, taking into account fluxes and reservoirs of their hydro-biogeochemical cycle assessed in WP2 & 3 and the management issues of WP4 – discussing the issue of scale.

Start of activity: 01 2012

Completion of activity: 06 2012

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.1.1 | Apply concept of circular economy |  | 01.12 – 06.12 |  |  |
| 5.1.2 |  |  |  |  |  |
| 5.1.3 |  |  |  |  |  |
| 5.1.4 |  |  |  |  |  |
| 5.1.5 |  |  |  |  |  |

5.2) Consideration synergistic and/or antagonistic effect on greenhouse gas sequestration of abatement action for reducing eutrophication.

Start of activity: 04 2012

Completion of activity: 12 2012

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.2.1 | Effects on greenhouse gas sequestration |  | 04.12 – 12.12 |  |  |
| 5.2.2 |  |  |  |  |  |
| 5.2.3 |  |  |  |  |  |
| 5.2.4 |  |  |  |  |  |
| 5.2.5 |  |  |  |  |  |

5.3) Based on the conceptual model of WP2 and the management analysis of WP4, develop a suitable nutrient management plan for Yuqiao Reservoir including a conceptual model for pre-warning of algal blooms and technical guidelines for health risk assessment and pollution control for MC in Yuqiao Reservoir – to be implemented in two demo villages.

Start of activity: 01 2014

Completion of activity: 09 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.3.1 | Prepare nutrient management plan |  | 01.14 – 09.14 |  |  |
| 5.3.2 |  |  |  |  |  |
| 5.3.3 |  |  |  |  |  |
| 5.3.4 |  |  |  |  |  |
| 5.3.5 |  |  |  |  |  |

5.4) Based on the model simulations in WP3 suggest adaptive measures to reduce the negative effects of climate change; taking into account land use and population figures

Start of activity: MM YYYY

Completion of activity: MM YYYY

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.4.1 |  |  |  |  |  |
| 5.4.2 |  |  |  |  |  |
| 5.4.3 |  |  |  |  |  |
| 5.4.4 |  |  |  |  |  |
| 5.4.5 |  |  |  |  |  |

5.5) A technical guideline of health risk assessment and pollution control for microcystins (MC) will be developed by physico-chemical and biochemical methods, also taking into account the discussion on distributive factors, fairness and justice in WP4, and drawing on environmental health impact assessment approaches22.

Start of activity: 04 2014

Completion of activity: 09 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.5.1 | Prepare technical guidelines |  | 04.14 – 09.14 |  |  |
| 5.5.2 |  |  |  |  |  |
| 5.5.3 |  |  |  |  |  |
| 5.5.4 |  |  |  |  |  |
| 5.5.5 |  |  |  |  |  |

5.6) Improve public awareness for nutrient pollution by means of a citizen training brochure for “What you can do to prevent nutrient pollution” to inform individuals/organizations about causes of and actions against eutrophication locally. This will be complemented by education and training courses for preventing eutrophication, thereby providing direct links to the issue of knowledge and learning processes.

Start of activity: 10 2013

Completion of activity: 09 2014

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.6.1 | Improve public awareness |  | 10.13 – 09.14 |  |  |
| 5.6.2 |  |  |  |  |  |
| 5.6.3 |  |  |  |  |  |
| 5.6.4 |  |  |  |  |  |
| 5.6.5 |  |  |  |  |  |

5.7) Give comprehensive and targeted presentations about the process of eutrophication, and governance/management issues for government officials at different levels.

Start of activity: MM YYYY

Completion of activity: MM YYYY

| No. | Sub activity | Description of activity | Timing | Responsible/participants | Resources |
| --- | --- | --- | --- | --- | --- |
| 5.7.1 |  |  |  |  |  |
| 5.7.2 |  |  |  |  |  |
| 5.7.3 |  |  |  |  |  |
| 5.7.4 |  |  |  |  |  |
| 5.7.5 |  |  |  |  |  |